Trip Checklist

|  |  | Director Responsibilities |  | Flag Waver Responsibilities | Trip Leader Responsibilities |  | Team Meetings |  | Student Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6 Months – 1 Year |  | Determine trips |  | Determine trip leaders | Review support letters |  |  |  | Order passport |
|  |  |  |  | Determine students and prep them for support letters |  |  |  |  | Be collecting 50 names and addresses |
| 3 Months – 6 Months |  | Determine trip leader |  | Ensure students order passports | Meet with the directors of discipleship and missions |  | “Trip Training” Biblical basis of missions Trip overviews Support letters written and sent |  | Attend meeting, Complete paperwork |
|  |  | Meet with traveling students at Discipleship retreat |  | Ensure students complete travel application |  |  |  |  | Send out support letters |
|  |  | Meet with flag waver (needs/plan) |  | Determine trip training date |  |  |  |  | Raise support (phone calls, meetings, fundraising nights) |
|  |  | Facilitate communication with field and team leader |  | Meet with director (needs/plan) |  |  |  |  |  |
| 3 Months Before Trip |  | Weekly support reports to flag waver |  | Manage Support-Raising Deadlines | Read Lightbearers White Paper* |  | “Team” Facilitator’s Guide – Pre-Trip Briefing* Team Values* (two options) |  | Raise support |
|  |  | CDC report to flag waver |  |  | Send CDC info to students |  |  |  | Attend meeting |
|  |  | Purchase visas as necessary |  |  | Manage Support-Raising Deadlines* |  |  |  | Pray with house |
|  |  | Manage Support-Raising Deadlines* |  |  | Coordinate in-country logistics with host |  |  |  | Get shots, if applicable |
| 2 Months Before Trip |  | Purchase tickets |  |  | Check with students on support raising (weekly) |  | “Country & Culture” Culture* Religion Overview* Country overview (BBC & Operation World) |  | Attend meeting |
|  |  | Weekly support reports to flag waver |  |  | Communicate with field personnel |  |  |  |  |
|  |  |  |  |  | Call parents, if needed |  |  |  |  |

|  |  | Director Responsibilities |  | Flag Waver Responsibilities | Trip Leader Responsibilities |  | Team Meetings |  | Student Responsibilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 Month Before Trip |  | Weekly support reports to flag waver |  |  | Learn to track trip expenses -Sample Trip Expense Report* |  | Team Specific Needs (prayer walking, partner requirements) |  |  |
|  |  | Request cash (ask flag waver for amount) |  |  | Read Team Evacuation Guidelines* |  | “Going” Packing List* Security Guidelines* |  | Attend meeting |
|  |  | Buy travel insurance, if applicable |  |  |  |  | Projects Project Proposal Guidelines* |  |  |
|  |  | Train trip leader on finances |  |  |  |  |  |  |  |
| 3 Weeks Before Trip |  | Meet with trip leader/flag waver |  | Meet with director/trip leader | Obtain insurance cards from LMI, if applicable |  |  |  |  |
|  |  |  |  |  | Meet with flag waver/director |  |  |  |  |
| 2 Weeks Before Trip |  |  |  |  |  |  |  |  |  |
| 1 Week Before Trip |  | Provide cash to flag waver |  |  | Prepare first aid kit |  |  |  |  |
|  |  |  |  |  | Obtain cash from flag waver |  |  |  |  |
|  |  |  |  |  | Obtain adapters from flag waver |  |  |  |  |
| On the Field |  |  |  | Send regular blog updates to prayer partners | Send regular blog updates to flag waver (bi-weekly) |  | Saying Goodbye* |  |  |
|  |  |  |  |  | Send regular (personal) updates to the Flag waver, Directors of Missions & Discipleship (every couple of days) |  | Facilitator’s Guide – Daily Debriefing* |  |  |
|  |  |  |  |  | Track money spent |  | Team Devotional Names of God* (optional) |  |  |
| On the Way Home |  |  |  |  |  |  | Team Debrief Debriefing* |  |  |
|  |  |  |  |  |  |  | Team Devotional Names of God* (optional) Post-Trip Devotional* (optional) |  |  |
| 2 Weeks After Trip |  | Report on support status |  |  | Contact team members one-on-one |  |  |  | Send thank you to donors |
|  |  | Offer scholarship application, if applicable |  |  | Report money spent |  |  |  |  |
|  |  | Award scholarships |  |  | Give copy of pictures/videos to Communications |  |  |  |  |
|  |  |  |  |  | Schedule debrief |  |  |  |  |
| 1 Month After Trip |  | Send thank you to donors |  |  |  |  | Facilitator’s Guide - Post-Trip Debriefing* |  | Attend debrief |
|  |  |  |  |  |  |  | Travel Evaluation* |  |  |
| As Needed |  | Send Withdrawal Letter to Supporters* |  |  | Notify Director/flag waver of withdrawing student |  | Complete homework from partners/meetings |  |  |
|  |  |  |  |  | Discuss with withdrawing student How to Be a Sender* |  |  |  |  |

*Denotes document on Dropbox.